## Sheet1
STAKEHOLDER ANALYSIS | [5 empty] | STAKEHOLDER ANALYSIS
Stakeholder | Role | Interest (1-10) | Influence (1-10) | Main Concern | How to Manage
Operations Head | Project Sponsor | 9 | 10 | ROI improvement and reversing B2B client attrition. | Monthly high-level status reports on KPI progress.
Warehouse Staff | Primary Users | 10 | 4 | App being too difficult to use during a busy shift. | Weekly "Walk-throughs" and focus on UI/UX simplicity.
Procurement Manager | Functional Lead | 8 | 7 | Accuracy of "Low Stock" alerts to prevent overstocking. | Involve in defining the "Reorder Point" logic.
IT Manager | Technical Lead | 6 | 8 | App security, data hosting, and system integration. | Regular technical reviews and alignment on tech stack.
Logistics Manager | Process Owner | 9 | 6 | Real-time visibility of orders leaving the warehouse. | Ensure the "Fulfillment Dashboard" meets their tracking needs.